## Scenario Comparison
Ministry of Justice — Digital Transformation Roadmap Scenario Comparison
Confidential — Draft for Steering Committee Discussion — August 2026
Fictional placeholder figures for project simulation purposes
Metric | Scenario A: Baseline (No Change) | Scenario B: Phased Modernization | Scenario C: Accelerated Cloud-First Transformation | Notes / Assumptions
Legacy Systems Retired | 0 | 3 | 6 | Scenario B retires Case Docket + Land Registry mainframes; Scenario C also retires Enforcement case tracker and moves to full cloud stack
Citizen Services Fully Digitized (of 12) | 0 | 7 | 12 | Includes e-filing, e-signature-enabled requests, and self-service Tabu extracts
Avg. Digital Maturity Score (of 5) | 1.9 | 3.1 | 4 | Blended score across the five directorates in scope
Total Implementation Cost (ILS) | 0 | 18500000 | 34000000 | Formula-driven, see below
Cloud Migration Cost Loading Factor | 0.35 | 0.35 | 0.35 | Consistent with 'Systems Inventory' workbook assumption
Total Fully-Loaded Program Cost (ILS) |  |  |  | Formula-driven, see below
Annual Legacy Maintenance Cost Avoided (ILS) | 0 | 2800000 | 5200000 | Estimated at 3 months salary + statutory per departing employee (placeholder — for staff redeployment support only)
Estimated Annual Efficiency Savings (ILS) |  |  |  | Formula-driven, see below
Payback Period (Years) |  |  |  | Formula-driven: Program Cost / (Savings)
Citizen Wait-Time Reduction (Avg.) | 0% | 35% | 60% | Based on comparable e-government transformation benchmarks (placeholder)
Cybersecurity / Data Risk | High (legacy exposure) | Medium | Low | Qualitative assessment — see Steering Committee deck for detail
Implementation Timeline (Months) | 0 | 14 | 22 | Includes vendor procurement, pilot rollout, and phased regional court deployment
Recommended Scenario |  | Scenario B — Phased Modernization
Rationale: | Best balance of citizen service improvement (~35% wait-time reduction) against implementation risk, procurement complexity, and budget cycle constraints. Scenario C's incremental gains do not justify the added program cost and multi-year disruption to court operations within the current planning horizon.