## Slide 1
HQ FINANCE ORGANIZATIONAL STREAMLINING
Executive Steering Committee Update
Meridian Strategy Partners | Confidential | September 30, 2026
Fictional placeholder data — internal project simulation

## Slide 2
Agenda
1
Engagement recap & objectives
2
Current-state diagnostic findings
3
Future-state scenario comparison
4
Recommendation & financial impact
5
Implementation roadmap & next steps

## Slide 3
Engagement Recap
HQ Finance Organizational Streamlining | Aug–Nov 2026
25
FTE in scope
2.8
Avg. span of control (current)
3
Sub-functions reviewed
8
Weeks to recommendation
Objective: Design an implementation-ready future-state organization for HQ Finance that improves span of control, removes role redundancy, and reduces payroll cost while managing employee relations risk.

## Slide 4
Diagnostic Findings
Thin spans of control
Multiple Senior Manager roles carry 2–3 direct reports versus an 5–7 benchmark, adding management layers without added value.
Overlapping sub-teams
Controllership's General Ledger and Statutory Reporting teams perform duplicative reconciliation work.
Junior-heavy analyst pool
11 of 25 roles are Analyst I/II level with less than 2 years tenure, indicating room for role consolidation.
Inconsistent grading
Similar-scope roles (e.g., Procurement Finance Analyst vs. FP&A Analyst) sit at different grade levels for comparable work.

## Slide 5
Future-State Scenario Comparison
Metric | A: Baseline | B: Moderate | C: Aggressive
Headcount | 25 | 22 | 19
Avg. Span of Control | 2.8 | 3.6 | 4.2
Est. Annual Savings | — | ~₪2.4M | ~₪4.7M
Employee Relations Risk | Low | Medium | High
Timeline to Implement | — | 4 months | 7 months
Fictional placeholder figures for project simulation purposes.

## Slide 6
Recommendation
Adopt Scenario B — Moderate Consolidation
Best balance of ~11% payroll cost reduction against employee relations risk and implementation complexity, within a manageable 4-month timeline.
₪2.4M
Annual run-rate savings
₪0.85M
One-time severance cost
4.3 mo
Payback period
Next step: Steering Committee approval to proceed to consultation phase per Section 5 of the Project Charter.

## Slide 7
Implementation Roadmap
Oct
Consultation & Notice
Formal consultation with affected employees per Israeli labor law
→
Oct–Nov
Role Transitions
Reassignment and onboarding into consolidated roles
→
Nov
Communication
All-hands briefing and updated org chart rollout
→
Dec
Stabilization
30/60/90-day check-ins, span of control re-validation
Confidential — Meridian Strategy Partners