## Slide 1
MERIDIAN STRATEGY PARTNERS
Mergers, Acquisitions & Integration Advisory
PGTech Integration — Steering Committee Update
Progress Against Day-1 / Day-100 Integration Plan
October 2026 — Monthly Steering Committee Meeting
This document contains fictional placeholder content prepared for internal project simulation purposes only.
Confidential — Meridian Strategy Partners

## Slide 2
Agenda
Confidential — Meridian Strategy Partners
• Deal timeline recap and closing status
• Due diligence findings — key updates since last review
• Synergy model refresh
• Post-merger org design — status and decisions needed
• Key talent retention — status
• Risks and open items

## Slide 3
Deal Timeline & Closing Status
Confidential — Meridian Strategy Partners
Milestone | Target Date | Status
NDA executed | May 18, 2026 | Complete
Due diligence complete | Sept 5, 2026 | Complete
Share Purchase Agreement signed | Sept 14, 2026 | Complete
Israeli Competition Authority filing submitted | Sept 21, 2026 | Complete
Regulatory clearance (expected) | Nov 10, 2026 | On Track
Closing | Nov 30, 2026 | On Track
Day-100 milestone review | Mar 10, 2027 | Not Started

## Slide 4
Synergy Model — Refresh
Confidential — Meridian Strategy Partners
• Total annual run-rate synergies (Year 3) estimated at USD 4.76M, in line with the Phase 2 model.
• One-time integration costs revised slightly upward to USD 2.93M (Year 1) after IT migration scoping.
• Estimated payback period: approximately 7.4 months from full run-rate.
Category | Year 1 | Year 3 (Run-Rate)
Revenue Synergies | $400K | $3.6M
Cost Synergies | $440K | $1.16M
One-Time Integration Costs | $2.93M | —

## Slide 5
Post-Merger Org Design — Status
Confidential — Meridian Strategy Partners
• Noam Bar-Lev confirmed for new VP, Digital Health Products role — offer accepted Sept 20, 2026.
• PGTech engineering (14 FTE), clinical/regulatory (4 FTE), and customer success (6 FTE) teams to be retained intact.
• Finance (3 FTE) and HR (2 FTE) shared-services absorption plan drafted — 5 roles flagged at risk of redundancy, consultation process to begin post-Closing per Israeli labor law.
• Decision needed from Steering Committee: timing of Finance/HR consolidation (Month 3 vs. Month 4 proposal).

## Slide 6
Key Talent Retention — Status
Confidential — Meridian Strategy Partners
Individual | Retention Grant | Status
Noam Bar-Lev (CEO) | $1.8M / 24-mo vest | Signed
Dana Levi (CTO) | $1.4M / 24-mo vest | Signed
Yael Ashkenazi (Clinical/Reg.) | $420K / 18-mo vest | In Negotiation
Omer Peretz (Lead Backend Eng.) | $380K / 18-mo vest | In Negotiation — flight risk
Tal Shapira (Customer Success) | $260K / 12-mo vest | Signed
Note: Omer Peretz has received two competing offers during the diligence period; HR recommends accelerating his retention conversation ahead of Closing.

## Slide 7
Risks & Open Items
Confidential — Meridian Strategy Partners
Risk / Open Item | Owner | Priority
Key engineer (Omer Peretz) retention not yet finalized | HR / Ilana Rosen | High
ICA regulatory clearance timeline | Legal (Ronit Sagi) | Medium
Finance/HR shared-services consolidation timing decision | Steering Committee | Medium
Customer data migration plan for PGTech CRM to Teva systems | IT / Platform Eng. | Medium
Day-1 communications plan for PGTech customers and payers | Corp Comms | Low

## Slide 8
Next Steps
Confidential — Meridian Strategy Partners
• Finalize Omer Peretz retention agreement by October 31, 2026.
• Confirm regulatory clearance status with ICA counsel — update expected early November.
• Steering Committee decision on Finance/HR consolidation timing at November meeting.
• Begin Day-1 readiness checklist walkthrough at next Steering Committee session.