MERIDIAN STRATEGY PARTNERS

Mergers, Acquisitions & Integration Advisory

PROJECT CHARTER & STATEMENT OF WORK

PGTech Acquisition — Due Diligence, Deal Support & Post-Merger Integration

This document contains fictional placeholder content prepared for internal project simulation purposes only.

| Client: | Teva Pharmaceuticals Ltd. — Digital Health & Innovation |
| --- | --- |
| Consultant: | Meridian Strategy Partners Ltd. |
| Engagement Sponsor: | Dr. Ilana Rosen, SVP Digital Health & Innovation |
| Engagement Lead: | Maayan Chen, Principal Consultant |
| Charter Date: | August 10, 2026 |
| Engagement Duration: | August 10, 2026 – February 28, 2027 (approx. 7 months) |

1. Background and Business Context

Teva Pharmaceuticals Ltd. ("Teva") has entered exclusive negotiations to acquire PGTech Health Solutions Ltd. ("PGTech"), a Herzliya-based remote patient monitoring (RPM) and digital health platform company founded in 2019. The acquisition supports Teva's strategic priority of expanding beyond traditional pharmaceuticals into connected-care and outcomes-based digital health offerings. Meridian Strategy Partners has been engaged to support financial and operational due diligence, deal structuring input, and post-merger integration planning.

2. Objectives

Validate PGTech's financial position, revenue quality, and cost structure ahead of signing.

Assess organizational fit and identify integration risks, including key-talent retention needs.

Develop a cost and revenue synergy model to inform deal economics and post-close targets.

Design a post-merger organizational structure for the combined Digital Health & Innovation unit.

Produce a Day-1 and Day-100 integration readiness plan.

3. Scope of Work — Phases

| Phase | Description | Target Timeline |
| --- | --- | --- |
| Phase 1 — Financial & Operational Due Diligence | Review of PGTech financials, cap table, contracts, IP, and HR data room; identification of key risks and DD findings. | Aug 10 – Sept 5, 2026 |
| Phase 2 — Deal Structuring & Synergy Modeling | Support on purchase price allocation, earnout structure, and development of the merger cost/synergy model. | Sept 8 – Sept 14, 2026 (through signing) |
| Phase 3 — Integration Design | Post-merger org structure design, retention plan for key PGTech talent, shared-services transition planning (Finance, HR, IT). | Sept 15 – Nov 15, 2026 |
| Phase 4 — Day-1 / Day-100 Readiness & Close Support | Communications planning, Day-1 checklist, integration governance cadence, Day-100 milestone tracking. | Nov 16, 2026 – Feb 28, 2027 |

4. Deliverables

Financial Due Diligence Summary (workbook)

Merger Cost & Synergy Model (workbook)

Proposed Post-Merger Org Chart

Key Talent Retention Plan

Day-1 / Day-100 Integration Playbook (presented to Steering Committee)

5. Governance

A joint Integration Steering Committee comprising representatives from Teva Corporate Development, Digital Health & Innovation, HR, Finance, and Legal, along with PGTech leadership (Noam Bar-Lev, Dana Levi) and Meridian Strategy Partners, will meet bi-weekly through Closing and monthly thereafter through the Day-100 milestone.

6. Fees

As set forth in the accompanying Consulting Services Agreement dated August 10, 2026: total contract value of USD 340,000 plus a USD 75,000 success fee payable upon signing of the Share Purchase Agreement.

This document is a fictional mock-up created for internal project simulation purposes and does not represent an actual document.

Confidential — Meridian Strategy Partners